## Summary
AI Law Portal: Project Tracker
Status as of 2026-10-08. Edit the Status column (dropdown) on the Frontend, Backend and AI sheets; this page recalculates.
Area | Done | In Progress | Not Started | Blocked | Total | % Done
Frontend | 15 | 1 | 14 | 0 | 30 | 50%
Backend | 16 | 0 | 21 | 1 | 38 | 42.11%
AI | 8 | 0 | 16 | 0 | 24 | 33.33%
Total | 39 | 1 | 51 | 1 | 92 | 42.39%
Progress by sprint
Sprint | Done | Total | % Done
Setup | 6 | 7 | 85.71%
Sprint 1 | 30 | 38 | 78.95%
Sprint 2 | 0 | 10 | 0%
Sprint 3 | 0 | 11 | 0%
Sprint 4 | 0 | 10 | 0%
Sprint 5 | 3 | 16 | 18.75%
Open items needing input from the project owner
1. eCourts API: base URL, auth method, endpoints, sample response (blocks BE-18 and all of Sprint 2).
2. Choose the first LLM and embedding model; embedding dimension is fixed at 768 in the schema (AI-09).
3. Confirm the pgvector package is installed on your Postgres server (BE-03).
Notes: Sprint 1 items were verified by hand on Postgres 16 + pgvector with a stub OpenAI-compatible endpoint. Automated tests are tracked as BE-17 and FE-14.

## Frontend
ID | Sprint | Feature / Task | Description | Status | Priority | Dependency / Notes | Owner | Target date
FE-01 | Setup | App shell | Vite + React 18 + Router + TanStack Query + Tailwind v4 + shadcn/ui base | Done | High
FE-02 | Setup | Sidebar layout and routes | Nav for all product areas; placeholders for later sprints | Done | High
FE-03 | Sprint 1 | Login and auth context | Animated split-screen sign-in with SVG illustration; JWT session, protected routes, sign out | Done | High | BE-04
FE-04 | Sprint 1 | Matters list and create form | List, status badge, create with new or existing client | Done | High | BE-09
FE-05 | Sprint 1 | Matter workspace: Overview (editable) | View/edit status, priority, lawyer, court, legal issues | Done | High | BE-09
FE-06 | Sprint 1 | Matter workspace: Timeline tab | Chronological event feed | Done | Medium | BE-11
FE-07 | Sprint 1 | Matter workspace: Documents tab | Upload, status polling while indexing, error display | Done | High | BE-12
FE-08 | Sprint 1 | Matter workspace: Ask AI tab | Question box, answer, numbered citations, disclaimer | Done | High | BE-14, AI-08
FE-09 | Sprint 1 | Matter workspace: Team tab | Add/remove matter members | Done | Medium | BE-10
FE-10 | Sprint 1 | Clients page | List, create, edit clients | Done | Medium | BE-08
FE-11 | Sprint 1 | Account page | Profile, time zone, working hours, notification and AI prefs | Done | Medium | BE-06
FE-12 | Sprint 5 | AI provider settings page | Admin form with Test connection; keys never shown | Done | High | BE-15
FE-13 | Sprint 1 | Matter tabs: Tasks, Hearings, Legal Intelligence, Communications, AI Activity | Currently placeholders pointing to their sprint | In Progress | Low | Built per sprint
FE-14 | Sprint 1 | Frontend automated tests | No unit or e2e tests yet (checked by hand with Playwright) | Not Started | Medium
FE-15 | Sprint 2 | Legal Intelligence page | Developments list, relevance, reviewed/dismissed actions | Not Started | High | BE-20, AI-12
FE-16 | Sprint 2 | Case comparison report view | My case vs judgment: same, different, impact, review | Not Started | High | AI-13
FE-17 | Sprint 3 | Tasks UI | Create, assign, due date, dependencies, archive | Not Started | High | BE-23
FE-18 | Sprint 3 | Calendar and hearings UI | Per matter and per user views | Not Started | High | BE-24
FE-19 | Sprint 3 | People page | Lawyers, workload, free/busy | Not Started | Medium | BE-25
FE-20 | Sprint 3 | Dashboard action center | Due/overdue, hearings, follow-ups, AI alerts | Not Started | High | BE-23, BE-24
FE-21 | Sprint 3 | Notifications UI | Inbox, mark read, actionable links | Not Started | Medium | BE-27
FE-22 | Sprint 4 | Approval inbox | Approve / reject pending agent actions | Not Started | High | AI-18
FE-23 | Sprint 5 | Settings: legal data, calendar, email, storage | Config forms with Test connection | Not Started | Medium | BE-31
FE-24 | Sprint 5 | Settings: agents and permissions | Policy editor, overrides, kill switch | Not Started | High | AI-16, AI-20
FE-25 | Sprint 5 | Settings: notifications, retention, API keys |  | Not Started | Low
FE-26 | Sprint 5 | Audit log viewer | Search by user, agent, action, resource | Not Started | Medium | BE-33
FE-27 | Sprint 5 | Analytics pages | Firm, legal intelligence and AI analytics | Not Started | Low | BE-34
FE-28 | Sprint 1 | Admin panel: Team & access | Create logins (invite link or temporary password), change roles, disable/enable, reset links, search and filters | Done | Medium | BE-07
FE-29 | Sprint 1 | Invite activation (register) flow | Paste invite link, verify, set name and password with strength meter, success animation | Done | High | BE-36
FE-30 | Sprint 1 | First-run firm setup | Two-step: firm name, then first admin account; refused once any user exists | Done | High | BE-36

## Backend
ID | Sprint | Feature / Task | Description | Status | Priority | Dependency / Notes | Owner | Target date
BE-01 | Setup | Repo layout and config | FastAPI app, pydantic settings, .env.example | Done | High
BE-02 | Setup | Database models | SQLAlchemy models for all entities, UUID PKs, pgvector chunks | Done | High
BE-03 | Setup | Initial Alembic migration | Includes CREATE EXTENSION vector | Done | High | Needs pgvector package on the server
BE-04 | Sprint 1 | Auth: login and /me | JWT, bcrypt hashing, seed script for first admin | Done | High
BE-05 | Sprint 1 | RBAC dependency | require_roles(); admin-only AI settings verified (403 for lawyer) | Done | High
BE-06 | Sprint 1 | Profile endpoint | PATCH /auth/me with time zone and HH:MM validation; role not editable | Done | Medium
BE-07 | Sprint 1 | User management API (admin) | List, create (invite or temp password), change role, disable/enable, reissue link; self-lockout and last-admin guards | Done | Medium
BE-08 | Sprint 1 | Clients API | List, create, update | Done | High
BE-09 | Sprint 1 | Matters API | List, create, get, patch; matter numbering | Done | High | Numbering uses row count; revisit for concurrency
BE-10 | Sprint 1 | Matter members API | List, add (409 on duplicate), remove; timeline-logged | Done | Medium
BE-11 | Sprint 1 | Case timeline | DB-backed events written by services | Done | High
BE-12 | Sprint 1 | Document upload and extraction | PDF/DOCX/TXT, local storage, per-page text, background task | Done | High
BE-13 | Sprint 1 | Chunking and embeddings storage | Chunks with doc/page/matter metadata in pgvector | Done | High | AI-05
BE-14 | Sprint 1 | Matter Q&A endpoint | POST /matters/{id}/ask | Done | High | AI-08
BE-15 | Sprint 5 | AI provider settings API | Encrypted keys, test endpoint (single provider) | Done | High
BE-16 | Sprint 1 | Access control per matter | Today any signed-in user can read any matter; restrict to members/assignee/partners | Not Started | High | Security hardening
BE-17 | Sprint 1 | Backend automated tests | No pytest suite yet (verified by hand with curl) | Not Started | High
BE-18 | Sprint 2 | eCourts provider adapter | ECourtsProvider implements LegalDataProvider | Blocked | High | Needs API base URL, auth, endpoints, sample response
BE-19 | Sprint 2 | Legal data normalization | Court, LegalCase, Party, Judgment, Order, Hearing, LegalProvision | Not Started | High | BE-18
BE-20 | Sprint 2 | Legal data sync and alerts | Manual + scheduled, dedupe by external ID, LegalDevelopment alerts | Not Started | High | BE-19
BE-21 | Sprint 2 | Matter-to-judgment matching service | Score storage with per-signal breakdown | Not Started | High | AI-12
BE-22 | Sprint 2 | Case comparison service | Stores comparison reports | Not Started | Medium | AI-13
BE-23 | Sprint 3 | Tasks API | CRUD, assignee, dependencies, archive; events to timeline | Not Started | High
BE-24 | Sprint 3 | Calendar and hearings API | CalendarProvider with local mock | Not Started | High
BE-25 | Sprint 3 | People and availability service | Free/busy from calendar + working hours | Not Started | Medium | BE-24
BE-26 | Sprint 3 | Scheduler | APScheduler for briefings, reminders, sync | Not Started | High
BE-27 | Sprint 3 | Notifications service | De-duplicated, actionable | Not Started | Medium | BE-26
BE-28 | Sprint 4 | Policy engine | ALLOWED / APPROVAL_REQUIRED / DISABLED, server-side | Not Started | High | AI-16
BE-29 | Sprint 4 | Approval requests API | Approve/reject re-checks policy, executes, audits | Not Started | High | BE-28
BE-30 | Sprint 4 | Temporary overrides and kill switch | Expiry checked at decision time | Not Started | High | BE-28
BE-31 | Sprint 5 | Integration settings APIs | Legal data, calendar, email, storage with test connection | Not Started | Medium
BE-32 | Sprint 5 | Model registry and routing API | Task-to-model mapping without code change | Not Started | Medium | AI-04
BE-33 | Sprint 5 | Audit log | Immutable record of every agent and user action | Not Started | High
BE-34 | Sprint 5 | Analytics endpoints | Only decision-driving metrics | Not Started | Low
BE-35 | Setup | Deployment and CI | Docker-free local run today; add CI for lint, tests, build | Not Started | Medium
BE-36 | Sprint 1 | Firm setup and invite API | /auth/setup, /auth/invite/{token}, /auth/accept-invite; tokens stored as SHA-256, single use, 7-day expiry | Done | High
BE-37 | Sprint 5 | Email delivery of invite and reset links | Today the admin copies the link; send it through EmailProvider | Not Started | Medium | Email integration
BE-38 | Sprint 1 | Login rate limiting | Throttle repeated failed sign-ins per email and IP | Not Started | Medium | Security hardening

## AI
ID | Sprint | Feature / Task | Description | Status | Priority | Dependency / Notes | Owner | Target date
AI-01 | Setup | Provider interfaces | LLM, Embedding, LegalData, Reranker, Email, Calendar interfaces | Done | High
AI-02 | Sprint 1 | OpenAI-compatible LLM provider | LangChain ChatOpenAI; works with Ollama, LM Studio, vLLM, OpenAI | Done | High | Verified against a stub endpoint only
AI-03 | Sprint 1 | OpenAI-compatible embeddings provider | Fixed dimension 768 in schema | Done | High | Verified against a stub endpoint only
AI-04 | Sprint 5 | Provider registry and encrypted config | Keys encrypted at rest, never returned to browser | Done | High
AI-05 | Sprint 1 | Chunking and embedding pipeline | Clean, chunk, embed, store with page metadata | Done | High
AI-06 | Sprint 1 | Hybrid retrieval | pgvector cosine + Postgres full-text, reciprocal rank fusion, top 6 | Done | High
AI-07 | Sprint 1 | Answer grounding rules | System prompt: only from sources, refuse if unsupported, no outcome prediction | Done | High
AI-08 | Sprint 1 | Cited matter Q&A | Answer with document/page citations | Done | High
AI-09 | Sprint 1 | Validate with a real LLM and embedding model | Choose models, confirm 768 dim, test on real legal PDFs | Not Started | High | Needs your model choice
AI-10 | Sprint 1 | RAG quality evaluation set | Questions with expected sources; measure citation accuracy and refusals | Not Started | Medium | AI-09
AI-11 | Sprint 1 | Scanned PDF / OCR support | Current extraction reads text PDFs only | Not Started | Medium
AI-12 | Sprint 2 | Matter-to-judgment matching | Multi-signal score: semantic, provision, court, case type, facts, recency | Not Started | High | BE-19
AI-13 | Sprint 2 | Case comparison prompts | Same / different / impact; never predict outcome; not legal advice | Not Started | High | AI-12
AI-14 | Sprint 2 | Reranker provider | Optional rerank step for retrieval and matching | Not Started | Low
AI-15 | Sprint 5 | Native Anthropic, Google, Azure providers | Settings lists them but only OpenAI-compatible is implemented | Not Started | Medium | AI-04
AI-16 | Sprint 4 | Agent tool registry | Controlled tools that call app services only, via policy engine | Not Started | High | BE-28
AI-17 | Sprint 4 | LangGraph agents | Daily Briefing, Matter Intelligence, Legal Research, Scheduling, Task | Not Started | High | AI-16
AI-18 | Sprint 4 | Execution modes and human approval | Suggest / Approval / Autonomous; default approval for risky actions | Not Started | High | BE-29
AI-19 | Sprint 4 | Scheduling flow | Find lawyer, check availability, propose, approve, create, notify, audit | Not Started | Medium | BE-25
AI-20 | Sprint 4 | Permission demo flow | Delete task blocked while DISABLED, works after policy change | Not Started | Medium | BE-28
AI-21 | Sprint 3 | Daily briefing generation | Per-user time from profile; stored result | Not Started | High | BE-26
AI-22 | Sprint 5 | Model routing per task | Summary, research, email, classification, embeddings, rerank | Not Started | Medium | BE-32
AI-23 | Sprint 5 | AI usage analytics and cost tracking | Calls, approvals, blocks, model usage | Not Started | Low | BE-34
AI-24 | Sprint 4 | Prompt-injection and data-leak guards | Treat document and eCourts text as untrusted; tool args validated server-side | Not Started | High | AI-16